## Sheet1
Task | Start Date | End Date
idea top brainstorming | 2024-08-27 | 2024-08-29
Platform Selection | 2024-09-02 | 2024-09-05
Backend Development (nodejs) | 2024-09-06 | 2024-09-16
Backend Development (fastapi) | 2024-09-17 | 2024-09-30
Frontend development(React Js) | 2024-10-01 | 2024-10-08
Frontend Development(AdminLogin) | 2024-10-09 | 2024-10-12
Frontend Development (Complete UI) | 2024-10-13 | 2024-10-17
Testing and Verification | 2024-10-18 | 2024-10-23
Modification and Optimization | 2024-10-24 | 2024-10-30
Preparing Final Report | 2024-10-31 | 2024-11-12